## RTM.APAC.Phase 0.Bus. Req.
BUSINESS REQUIREMENTS DOCUMENT (Phase 0) for PHS (Account # 99930) Go-Live
1. Mapping of Order Template for Bulk Upload from RTM to Quincus
2. Development of BobJ Report and placing it in FTP
3. BOT development to upload Order Template to Quincus
4. Mapping of Milestones Template for Bulk Upload from Quincus to RTM
5. Quincus to place the Milestones Template to FTP Location
6. Development of Cron Job to upload Quincus Milestone Data to RTM
BUSINESS REQUIREMENTS DOCUMENT (Phase 1) for PHS (Account # 99930)
1. Development of 'Get Order Tracking URL', API to access Quincus GPS Tracking (Qship), from CFW

## RTM.APAC.Phase 0.Project Plan
|  | Color Legend | Not Started | In Progress | Complete | Overdue
Milestone # | Phase | Milestone Summary | Owner | Status | Planned Start Date | Actual Start date | Planned End Date | Actual End Date | Comments
1 | 1 | Quincus - Provide Order Upload Template | Afif | Complete | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
2 | 1 | UPS - Provide Milestones Template for Bulk Upload from Quincus to RTM | Ryan Chi/Sandya/Henry | Complete | 2022-06-27 | 2022-06-27 | 2022-07-01 | 2022-07-01
3 | 1 | UPS - Mapping of Order Template for Bulk Upload from RTM to Quincus | Sandya/Henry/Ryan Chi | In Progress | 2022-06-27 |  | 2022-07-19
4 | 1 | UPS - BobJ Report Development | GowriShankar/Raghu Maity | In Progress | 2022-07-11 | 2022-07-11 | 2022-07-22
5 | 1 | UPS - Set-up of SFTP Account for Quincus | GowriShankar | Complete | 2022-07-06 | 2022-07-06 | 2022-07-13 | 2022-07-12
6 | 1 | UPS - BobJ UAT Deployment | GowriShankar | Not Started | 2022-07-22 |  | 2022-07-22
7 | 1 | UPS - APAC Bot Development to upload Orders to Quincus | Ryan Chi | Complete | 2022-07-11 | 2022-07-11 | 2022-07-15 | 2022-07-15
8 | 1 | UPS - APAC BOT UAT Deployment to upload Orders to Quincus | Ryan Chi | In Progress | 2022-07-18 | 2022-07-18 | 2022-07-22
9 | 1 | Quincus - Confirmation on ability to receive RTM orders, upload and create correctly in Quincus | Rian Simbahan/Alvin Condes/Afif | Not Started | 2022-07-18 |  | 2022-07-22 |  | 7/7: Will be evaluated as a part of UAT.
10 | 1 | Quincus - Place the POD Template in UPS FTP Site | Afif | In Progress | 2022-07-04 |  | 2022-07-22 |  | 7/7: Q will provide a sample template populated with Data. At Risk Task due to delivery ETA. Will will advise on an ETA of when he is able to do this.
11 | 1 | UPS - cron job Development and deployment | Sandya | In Progress | 2022-07-15 |  | 2022-07-22
12 | 1 | UPS - cron job UAT deployment | Koushik/Sandya | Not Started | 2022-07-24 |  | 2022-07-24
13 | 1 | UPS - UAT | Rian Simbahan/Alvin Condes | Not Started | 2022-07-24 |  | 2022-07-29 |  | 7/7: Jack to align with his team to provide a copy of the UAT Test Plan by highlighting the items that are required to pass to meet the Aug 1st Go-Live with PHS
14 | 1 | UPS - UAT sign-off | Rian Simbahan/Alvin Condes | Not Started | 2022-07-29 |  | 2022-07-29
15 | 1 | UPS - Production Deployment | Sandya | Not Started | 2022-08-01 |  | 2022-08-01
16 | 2 | UPS-Quincus - Development of 'Get Order Tracking URL API', to access Quincus GPS Tracking (Qship), from CFW | Afif/Sandya | Not Started
17 | 2 | UPS - Develop and deployment of the cron job | Sandya | Not Started
18 | 2 | UPS - RTM QA Testing of 'Get Order Tracking URL API' | Sandya | Not Started
19 | 2 | UPS - RTM Regression Testing | Sandya | Not Started
20 | 2 | UPS - UAT deployment | Koushik/Sandya | Not Started
21 | 2 | UPS - UAT | Dannell Wong | Not Started
22 | 2 | UPS - UAT sign-off | Dannell Wong | Not Started
23 | 2 | UPS - Production Deployment | Sandya | Not Started

## Bus.Req. RTM-APAC Integration (hidden)
BUSINESS REQUIREMENTS DOCUMENT

## RTM.APAC Integration.Plan (hidden)
Color Legend | Not Started | In Progress | Complete | Overdue
Milestone | BRD Requirement # | Owner | Status | Planned Start Date | Actual Start date | Planned End Date | Actual End Date | Comments

## Action Item Tracker
| Color Legend | Not Started | In Progress | Complete | Overdue | Revisit
Open Date | Category | Priority | Description | Assigned To | Status | Planned Completion Date | Actual Completion Date | Comments
2022-04-21 | Technical | Medium | Q to evaluate the language feature on local maps | William/Afif | Overdue | 2022-04-29
2022-04-21 | Technical | Medium | RTM to evaluate the local language and local currency functionality as it relates to API transmission to Quincus for Master Data configuration for Vendor and Customer | William/Afif | Overdue | 2022-04-29
2022-04-21 | Business Requirements | Medium | Map the EC requirements in the APAC BRD | Sheela/Brandy | Complete | 2022-04-29
2022-04-21 | Technical | Medium | Provide additional Vendor TMS details to evaluate integration needs | Jack | In Progress | 2022-04-29 |  | 4/29: already get the basic infromation, more detail information will get after Phase 1 go-live
2022-04-21 | Business Requirements | Medium | Reach out to the local Singapore APAC team for coordination of in-person sessions | William | Complete | 2022-04-29
2022-04-21 | Business Requirements | Medium | Confirm if PHS is using Symphony or Harmony | AJ | Complete | 2022-04-29 |  | 5/23: PHS is using Harmony. Meeting scheduled for next steps.
2022-05-19 | Technical | Medium | How are incorrect addressess via B2B handled | William/Afif | Overdue | 2022-05-24 |  | 5/19: Not in Q scope for Phase 1 per William
2022-05-19 | Technical | Medium | Send completed RTM BRD back to UPS IT | Jack | Complete | 2022-05-27
2022-05-19 | Technical | Medium | Provide feedback on Quincus BRD to the APAC Team | Afif/William | Overdue | 2022-05-25 |  | 6/6: Per Jack, William is working on the SOW in which the BRD will be embedded. ETA of delivery is one week. 6/2: Afif will align with William and provide feedback.
2022-05-23 | Technical | Medium | Demo of the RTM UI features deployed in production so far | Sandya | Overdue | 2022-05-24
2022-05-23 | Business Requirements | Medium | Feedback from APAC team on how we are feeding Vendor Assignment feedback into RTM from Quincus | Jack/Prashant/William | Complete | 2022-06-07 |  | 6/2: Vendor assignment will take place in RTM, Q will then automate to assign the task to the right Vendor in Phase 1. Teams will align on the next steps in the next call.
2022-05-23 | Business Requirements | Medium | Confirm how to differenciate the EC and Post-Sales APAC integrations (Data tags on payloads) | Jack/Prashant/William | Complete | 2022-06-07 |  | 6/2: This discussion is contingent on RTM team updating the API document to include APAC scope.
2022-05-26 | Business Requirements | Medium | Update this in RTM UI/UX BRD - Quincus BRD - R01.F is not in scope for RTM Display and will be done via Qship | Sandya | Overdue | 2022-06-07
2022-05-31 | Business Requirements | Medium | Provide Q an updated API document to include APAC | Sandya | Complete | 2022-06-03
2022-05-31 | Business Requirements | Medium | How are Quincus and UPS managing inventory items for Post Sales business | Afif/William | In Progress | 2022-06-13 |  | 6/9: William will align with Afif. 6/2: Afif will provide feedback after alignment with his team.
2022-06-02 | Business Requirements | Medium | Is Consolidation feature required? | Ken | Complete | 2022-06-02 |  | 6/2: Not needed for now per Ken and can be considered as enhancement feature down the road.
2022-06-06 | Business Requirements | Medium | Can Korea Integration be removed from the Scope of Phase 1 Quincus delivery? | Jack/William | Complete | 2022-06-13 |  | 6/9: Per Jack, this will remain in scope. While the team will pursue a discussion with PHS, Q to continue planning to include this in scope. 6/6: Jack will align internally and provide feedback to Brandy and Sheela. 7/8: Korea integratio should be in Phase 1, however due to timeline and EC seleect the Scaniors 2 for the development, there will not Korea on board in Phase1.
2022-06-07 | Business Requirements | Medium | Instead of building Qship, is it easier to build a tracking URL link in RTM CFW for dispatch page via an API call? | William | Complete | 2022-06-08 | 2022-06-09 | 6/9: William has advised that building Qship and a tracking link in is the proposed go-forward solution. UPS team is aligned.
2022-06-09 | Business Requirements | Medium | Can tracking URL be pulled in as part of Q July deliverable? | William | Complete | 2022-06-13 |  | 7/7: Confirmed yes by Q.
2022-06-09 | Business Requirements | Medium | Fesability of Q supporting PHS searching with Order # (Ref on Order) | William | In Progress | 2022-06-13 |  | As long as we keep PHS Ref No in Quincus Reference Id, we will be able to search it via qship
2022-06-09 | Business Requirements | Medium | Provide the RTM team with an updated template with mandatory fields in alignment with Quincus | Jack | Complete | 2022-06-13 |  | Discussion to match RTM's Bobj Report vs Quincus Order Upload Template is In Progress. Next session TBA. 6/24: share the template with compusary field with Sandya.
2022-06-15 | Business Requirements | Medium | Is Q storing 3 months of historical data (GPS bread-crumbs) sufficient? | Jack | Complete | 2022-06-15 |  | 7/8:Data in Q_ship, 3 months ok, but for shipment data, keep 3 years.
2022-06-16 | Business Requirements | Medium | Is the Quincus language traslation UTF-8 Compliant? | Afif/William | Complete | 6/20/222 |  | Database confirm UTF-8 compliant
2022-06-16 | Business Requirements | Medium | Is the Quincus Bulk Upload File UTF-8 Compliant? | Afif/William | Complete | 6/20/222 |  | Bulk-upload files are also UTF-8 compliant (afif to share latest version)
2022-06-16 | Business Requirements | Medium | Break down the Quincus BRD by phases for Quincus sign-off on Phase 1 | Jack/Ken | Complete | 6/21/222
2022-06-16 | Business Requirements | Medium | Share the UPS Recepient email for POD for UAT and Prod | Jack | Complete | 2022-07-07 |  | 7/8: for development phase, it will be Ryan's UPS email; after go-live, it will be CCC group email.

## Risks
Color Legend | Not Started | In Progress | Complete | Overdue
Summary | Next Steps | Owner | ETA | Status | Comments

## Project Team
Title | Name | Email | Timezone
IT Solutions Manager | Brandy Young | brandyyoung@ups.com | EST
RTM Development Lead | Koushik Rajagopalan | krajagopalan@ups.com | EST
RTM Delivery Lead | Sandya Kadam | sandyakadam@ups.com | EST
RTM Business Analyst | Shruthi Arunkumar | sarunkumar@ups.com | IST
RTM Delivery Manager | Prashant Kirangi | prashantkirangi@ups.com | EST
IT Project Manager | Sheela Shenoy | sheelashenoy@ups.com | EST
Business Solutions/ Program Manager | Jack Yang Hong Peng | yanghongpengjack@ups.com | SGT